## Slide 1: CIROH DocuHub Chatbot on AWS
Migration status update | October 5, 2026
Live: https://d1ex71xvx5s2ao.cloudfront.net
Notes: Status of the Azure-to-AWS migration of the CIROH DocuHub chatbot, following the AWS Migration Plan V2. The app is live on AWS today.

## Slide 2: The chatbot is live on AWS, end to end
58 / 58
AWS resources deployed, zero failures
13,749
text chunks embedded across 563 documents
8-10 s
answer time (API limit is 29 s)
~1¢
per question on Claude Haiku 4.5
Remaining work is cleanup, tuning, and the cutover from Azure.
Notes: Everything in the migration plan's target architecture is running. The test numbers come from the end-to-end smoke test through CloudFront and from the live chat UI.

## Slide 3: What is running in AWS today
Browser
React chat UI
CloudFront + WAF
CDN, rate limit, managed rules
API Gateway
HTTP API, throttled
Lambda
FastAPI + hybrid RAG
Amazon Bedrock
Claude Haiku 4.5, Titan Embeddings V2, Guardrail
Aurora Serverless v2
PostgreSQL + pgvector via RDS Data API
us-east-1, one CloudFormation stack (CirohStack)
Deployed with AWS CDK from CloudShell, no local keys
Idle parts scale to zero (database pauses)
Notes: This matches Figure 1 of the migration plan, with one change: WAF sits on CloudFront because AWS WAF cannot attach to API Gateway HTTP APIs.

## Slide 4: Done: infrastructure and access
Infrastructure
CDK bootstrapped in us-east-1
CirohStack deployed: 58 resources
WAF rate limit + AWS managed rules
Bedrock guardrail for off-topic requests
Budgets ($60/mo) + email alerts
Access and documentation
Deploy path that needs only console login
Claude Haiku 4.5 enabled in Bedrock
IAM permission policies written for admins
Beginner deployment guides (3 docs)
Rebuild + validation scripts in the repo
Notes: The university account policy does not allow an access portal URL or access keys, so the whole deployment runs from AWS CloudShell inside the console. Docs: AWS_DEPLOYMENT.md, AWS_DEPLOYMENT_CLOUDSHELL.md, AWS_PERMISSIONS.md.

## Slide 5: Done: knowledge base rebuilt without Azure
Chart: 563 documents loaded into Aurora
| Publications | CIROH Hub pages | Datasets | GitHub repos
Documents | 228 | 242 | 42 | 51
Same steps as PopulateDB.ipynb, run on the repo's JSON and .mdx files
242 Hub page summaries regenerated with Claude (about $2, once)
13,749 chunks embedded with Titan V2 (1024 dimensions)
Validation: 0 orphan chunks, 0 missing embeddings
Notes: Azure database credentials were not available, so the corpus was rebuilt from the source files the notebook used to fill Azure. If Azure holds newer content than the repo files, it is not included yet (see pending).

## Slide 6: Done: retrieval and end-to-end tests pass
Test | Result | Status
Search: "What is NextGen In A Box?" | Top match: NGIAB page (distance 0.25) | Pass
Search: "Access to CIROH cloud computing?" | Top match: CIROH AWS Account (0.27) | Pass
Off-topic: "Write an essay on the French Revolution" | Score 0.88, refused in 0.3 s, no model call | Pass
End to end through CloudFront | 2 questions answered in 9.7 s and 8.1 s | Pass
Live chat UI in the browser | Answer with sources and question-type label | Pass
Notes: Distances are cosine distances from pgvector: lower is closer. The off-topic gate rejects anything above 0.7 before the model is called.

## Slide 7: Done: issues found and fixed on the way
WAF placement
Moved to CloudFront: WAF cannot attach to HTTP APIs
Model ID
Claude Haiku 4.5 needs the us. inference profile ID
Lambda crashes
Removed openai import; telemetry now logs to CloudWatch
Data API queries
Array params, jsonb/vector casts, wait for DB wake-up
Frontend URL
Production build was calling 127.0.0.1
Deploy blockers
Invalid rule text, leftover log group, import path
Notes: The code from the earlier CDK commit would not have deployed or answered questions as written. All fixes are in the local repo and were verified with local synth/tests and the live deploy.

## Slide 8: Cost: small, but above the plan's estimate
Chart: Estimated monthly cost (USD)
| Idle | 1,000 questions | 10,000 questions
Estimated monthly cost (USD) | 12 | 22 | 112
~1¢
per question measured, vs 0.3¢ in the plan
Hybrid routing makes 3 model calls and sends about 8,000 tokens of context per question
Idle cost is mostly the WAF ($7/month)
Alerts at 50/80/100% of a $60/month budget
Notes: Monthly figures are estimates: idle about $8-15 plus about $0.01 per question. The measured question in the UI used 7,923 tokens, about $0.0101. At 10,000 questions a month the bill would pass the $60 budget, so cost tuning is on the pending list.

## Slide 9: Pending: actions and owners
Action | Owner | Priority
Confirm the AWS alert email subscription | Prajwal | High
Commit fixes and docs to the aws-bedrock-migration branch, open a PR | Prajwal | High
Activate the "Project" cost allocation tag (management account) | Ben | Medium
Cut per-question cost (smaller context, fewer classifier calls) | Prajwal | Medium
Tune off-topic threshold and WAF limits with real questions | Prajwal + team | Medium
Check Azure DB for content newer than the repo files, then sync | Team | Medium
Delete the empty leftover log group from the first attempt | Prajwal | Low
Notes: The log group is /aws/lambda/ciroh-docuhub-ask in CloudWatch: empty and free, but worth removing. Azure sync needs someone with the Azure database password: run migrate_to_bedrock.py --export, then load the file.

## Slide 10: Later: the road to production
1
Team testing
Real questions from the team; log wrong or missing answers
2
Tune
Threshold, WAF limits and cost, using that feedback
3
Harden
env_name=prod (keeps data on delete), custom domain, grounding check
4
Cut over
Point users to AWS, keep Azure read-only briefly, then retire it
Optional: keep the database warm (min 0.5 ACU, about +$43/month) to remove the ~15 s first-question delay; automate ingestion once the notebooks become scripts.
Notes: Step 1 is where we are now. The production switches are each a one-line setting in infra/cdk.json plus a redeploy, except the custom domain, which needs Route 53 and a certificate.

## Slide 11: Ready for team testing
Try it: https://d1ex71xvx5s2ao.cloudfront.net
Ask real CIROH questions this week and send any wrong or missing answers
Notes: The first question after a few idle minutes can take about 15 seconds longer while the database wakes up.